## Slide 1
Stamford ERP Project
Board of Finance
Project Update
July 14, 2022
Innovating Since 1641

## Slide 2: Agenda
Progress-to-date
  Project Schedule
  Current Activities
  Budget Status
Breadth of the Project
Review Open Issues and Risks
  Change Order Approval Request

## Slide 3
Progress-to-date

## Slide 4
Project Schedule

## Slide 5
Conference Room Pilot 2 (CRP2)
  Stamford team hands-on configuration testing
  Scripted tests – over 200 scripts
  No converted data
  No interfaces
  Multiple 3-hour sessions for each module
  Purpose is to confirm the configuration is as expected based on
    Configuration Workbooks
    Configuration Documents
    CRP1 – conducted by Sierra-Cedar
  Initial hands-on experience for the Stamford team
  Scheduled from June 15 – July 13
The next major activity is System Integration testing starting in mid-August
Current Activities

## Slide 6: Project Budget Status
Estimated Capital Cost by Fiscal Year |  |  |  |  |  |  |  |  |  | 
Cost Category | FY 21/22 | FY 22/23 | FY 23/24 | FY 24/25 | Total Budget | Adjustments | Actuals-to-Date | Unexpended | Encumbered | Available Balance
ERP Implementation | $1,997,500 | $1,402,500 |  |  | $3,400,000 |  | ($1,772,500) | $1,627,500 | $1,627,500 | $0
L&P Implementation |  | $470,000 | $509,000 |  | $979,000 |  |  | $979,000 | $979,000 | $0
Cashiering Implementation | $88,500 | $53,260 |  |  | $141,760 |  | ($41,020) | $100,740 | $100,740 | $0
ERP Implementation Contingency |  | $100,000 |  |  | $100,000 |  |  | $100,000 |  | $100,000
Total Implementation | $2,086,000 | $2,025,760 | $509,000 | $0 | $4,620,760 | $0 | ($1,813,520) | $2,807,240 | $2,707,240 | $100,000
ERP Software Subscriptions | $198,100 | $330,013 |  |  | $528,113 |  | ($275,390) | $252,723 | $252,723 | $0
L&P Subscriptions |  | $123,525 | $164,700 | $137,250 | $425,475 |  |  | $425,475 | $425,475 | $0
CanAm Subscriptions | $16,635 | $49,905 |  |  | $66,540 |  | ($66,540) | $0 | $0 | $0
Total Subscriptions | $214,735 | $503,443 | $164,700 | $137,250 | $1,020,128 | $0 | ($341,930) | $678,198 | $678,198 | $0
ERP Travel Expense (estimated) | $50,000 | $35,000 |  |  | $85,000 |  |  | $85,000 |  | $85,000
L&P Travel Expense (estimated) |  | $35,000 | $50,000 | $25,000 | $110,000 |  |  | $110,000 |  | $110,000
Cashiering Travel Expense (estimated) | $10,000 | $15,000 |  |  | $25,000 |  | ($1,802) | $23,198 | $23,198 | $0
Total Travel | $60,000 | $85,000 | $50,000 | $25,000 | $220,000 | $0 | ($1,802) | $218,198 | $23,198 | $195,000
ISG Project Management | $399,000 | $399,000 | $399,000 | $280,000 | $1,477,000 |  | ($631,750) | $845,250 | $845,250 | $0
ISG Consulting Conversion & Interface Resources | $208,000 | $92,000 |  |  | $300,000 | $146,400 | ($96,700) | $349,700 | $349,700 | $0
City Overtime | $200,000 | $450,000 | $200,000 | $150,000 | $1,000,000 |  |  | $1,000,000 |  | $1,000,000
Equipment Acquisition | $118,000 | $66,000 | $0 | $0 | $184,000 |  |  | $184,000 |  | $184,000
Fleet Maintenance and Fuel Dispensing Software | $592,000 | $0 | $0 | $0 | $592,000 |  |  | $592,000 |  | $592,000
Ceridian Dayforce Integration |  |  |  |  |  | $80,000 |  | $80,000 |  | $80,000
Contingent 3rd Party Consulting - Innovations |  | $750,000 | $750,000 | $500,000 | $2,000,000 | ($226,400) |  | $1,773,600 |  | $1,773,600
Total Other | $1,517,000 | $1,757,000 | $1,349,000 | $930,000 | $5,553,000 | $0 | ($728,450) | $4,824,550 | $1,194,950 | $3,629,600
Contingency |  |  |  |  | $500,000 |  |  | $500,000 |  | $500,000
Total ERP by FY | $3,877,735 | $4,371,203 | $2,072,700 | $1,092,250 | $11,913,888 | $0 | ($2,885,702) | $9,028,186 | $4,603,586 | $4,424,600

## Slide 7
Breadth of the Project

## Slide 8
The Enterprise Nature of the Project
Inbound from City systems to Oracle
Outbound from Oracle to City systems
Each Integration Requires
Analysis
Design
Functional Specification
Technical Specification
Development
Testing

## Slide 9
Continuity of Data
Each Integration Requires
Analysis
Design
Functional Specification
Technical Specification
Development
Testing

## Slide 10
Risks and Issues

## Slide 11: Key Risk – Ceridian Dayforce Integration
  Risk Factors
    The Dayforce system was implemented as one system with separate high-level configurations for BOE and the City resulting in one system used in two different ways
    Some implemented workarounds make it more difficult to make the required changes for example, embedding the sub-department in the job title
    In addition, Dayforce is inflexible and has difficulty handling routine chart of accounts changes
    The level of effort involved in the changes necessary to integrate DayForce with Oracle Cloud may result in the integration not being ready for System Integration Testing
    Every integration activity is twice the effort – once for BOE and once for the City
    Currently working on the Ceridian change order for this work
Mitigating Activities
    Stamford is using an existing SOW with Ceridian
    Ceridian has assigned a project manager
    BOE and the City HR and Payroll managers have been involved in the planning
    A project plan will be developed to manage the process.
    Contingency plan is to develop a traditional crosswalk for the interface

## Slide 12: Key Risk – Ceridian Dayforce Integration
  Ceridian Change Order
    For completion of the work to more fully integrate Ceridian with Oracle
      SRS #1 changes to the Ceridian chart of accounts
      SRS #2 changes to the payroll interface extract files
    An additional test environment to isolate this work from other ongoing testing by HR and Payroll
    This work will be funded from the ERP project.
  Change order amount
  Modification of the HR / Payroll system*: $69,480
*Includes $14,400 contingency

## Slide 13
Questions?