## Slide 1
Stamford ERP Project
Board of Finance
Project Update
November 28, 2022
Innovating Since 1641

## Slide 2: Agenda
Project Update
  Review project decisions-to-date – Business Processes
  Project Schedule – Conversion Status
  Budget Status
  Requests of the Board

## Slide 3: Business Process Change
Prior Year Purchase Orders
  In H T E, POs were carried forward to the new year in a separate bucket that did not effect the budget for that year
  In Oracle, the funds to pay carry forward POs is nor ij a separate bucket so the spending authority is adjusted to cover the extra cost in the new year
  Current Process
    Carryforward all open Purchase Orders to the next year
    Treat as accounting encumbrances not as budgetary encumbrances
    Record the expenses in the GL for invoices paid but no reduction of budget
  Oracle Process Differences
    POs can be carried forward with or without corresponding budget capacity
    POs and related payments consume current year budget regardless of budget capacity
  Proposed new Process
    Allow payment of prior year POs received by June 30 through August 15 of new year
    Cancel open POs not received by June 30 of the fiscal year; or
    Departments may provide justification to carry POs forward into the next year including increasing the new year budget to cover the POs carried forward – Board approval required

## Slide 4: Business Process Changes
FY2023 Impact
  Prior Year Purchase Orders
    The current process was already completed in H T E
    When we convert them into Oracle, they will consume FY2023 budget the need for which was not anticipated in the approved budget
FY22 Initial Rollover Encumbrance | $7,537,493 | 
Cancelled POs | $1,064,018 | 
Net Amount to Balance Oracle Budget | $6,473,475* | 
*$2,293,604 Has been paid to vendors

## Slide 5
Project Schedule
User Acceptance Testing Conversion Status
  Significant volume of budget errors
    We didn’t fully understand the impact of prior year POs until we started converting for UAT
    The prior year POs have caused several downstream issues with later conversions
    We have been “fixing” the issues to make the conversions load, but the fixes are not something we want to do in the production conversion
  Conversion Restart
    Adjust budget to accommodate prior year encumbrances and expenses in FY 2023 with approval of the Board
    Focus will be on more thorough data validation before it is loaded into Oracle
    Issues that are true conversion logic or configuration related will be isolated and fixed in the conversion process
    Converted data loaded into Oracle the process will be cleaner
  Therefore, we propose delaying our go-live to March 1, 2023 and adding 2 months of vendor support

## Slide 6
Project Schedule / Current Activities
November
December
January
Revised Go-Live Schedule
February
Validate Conversions and Interfaces
UAT
Train the Trainer
End User Training / Labs
Blackout Period
2/10
Cutoff
Final Transactions Submitted to Administration
3/1 Go-live
No department Transactions Processed In H T E or Oracle
March
2/15
Final checks, ACH, and POs from H T E
Validate Conversions and Interfaces
UAT
Train the Trainer
End User Training
Blackout Period
End User Labs
Original Go-live

## Slide 7
Cost Impact Estimate
ISG Conversion and Interface support: $56,000
Oracle / Sierra-Cedar: (Implementation & Extended Support) $1,500,000
CanAm: $4,100
      Total $1,560,100

## Slide 8: Project Budget Status
Capitalized Implementation, Subscription, Travel, and Other Cost |  |  |  |  |  |  |  |  |  | 
Estimated Capital Cost by Fiscal Year |  |  |  |  |  |  |  |  |  | 
Cost Category | FY 21/22 | FY 22/23 | FY 23/24 | FY 24/25 | Total Budget | Adjustments | Actuals-to-Date | Unexpended | Encumbered | Available Balance
ERP Implementation | $1,997,500 | $1,402,500 |  |  | $3,400,000 | $159,000 | ($2,333,875) | $1,225,125 | $1,225,125 | $0
L&P Implementation |  | $470,000 | $509,000 |  | $979,000 |  |  | $979,000 | $979,000 | $0
CanAm Cashiering Implementation | $88,500 | $53,260 |  |  | $141,760 |  | ($99,758) | $42,002 | $42,002 | $0
ERP Implementation Contingency |  | $100,000 |  |  | $100,000 |  |  | $100,000 |  | $100,000
Total Implementation | $2,086,000 | $2,025,760 | $509,000 | $0 | $4,620,760 | $159,000 | ($2,433,633) | $2,346,127 | $2,246,127 | $100,000
ERP Software Subscriptions | $198,100 | $330,013 |  |  | $528,113 |  | ($553,148) | ($25,035) | ($25,035) | $0
L&P Subscriptions |  | $123,525 | $164,700 | $137,250 | $425,475 |  |  | $425,475 | $425,475 | $0
CanAm Cashiering Subscriptions | $16,635 | $49,905 |  |  | $66,540 |  | ($133,080) | ($66,540) | ($66,540) | $0
Total Subscriptions | $214,735 | $503,443 | $164,700 | $137,250 | $1,020,128 | $0 | ($686,228) | $333,900 | $333,900 | $0
ERP Travel Expense (estimated) | $50,000 | $35,000 |  |  | $85,000 |  |  | $85,000 |  | $85,000
L&P Travel Expense (estimated) |  | $35,000 | $50,000 | $25,000 | $110,000 |  |  | $110,000 |  | $110,000
CanAm Cashiering Travel Expense (estimated) | $10,000 | $15,000 |  |  | $25,000 |  | ($1,802) | $23,198 | $23,198 | $0
Total Travel | $60,000 | $85,000 | $50,000 | $25,000 | $220,000 | $0 | ($1,802) | $218,198 | $23,198 | $195,000
ISG Project Management | $399,000 | $399,000 | $399,000 | $280,000 | $1,477,000 |  | ($798,000) | $679,000 | $679,000 | $0
ISG Consulting Conversion & Interface Resources | $208,000 | $92,000 |  |  | $300,000 | $146,400 | ($446,400) | $0 | $0 | $0
City Overtime | $200,000 | $450,000 | $200,000 | $150,000 | $1,000,000 |  |  | $1,000,000 |  | $1,000,000
Equipment Acquisition | $118,000 | $66,000 | $0 | $0 | $184,000 |  |  | $184,000 |  | $184,000
Fleet Maintenance and Fuel Dispensing Software | $592,000 | $0 | $0 | $0 | $592,000 |  | ($26,625) | $565,375 | $0 | $565,375
Ceridian Dayforce Integration |  |  |  |  |  | $77,400 | ($15,345) | $62,055 | $62,055 | $0
Contingent 3rd Party Consulting - Innovations |  | $750,000 | $750,000 | $500,000 | $2,000,000 | ($226,400) | ($7,470) | $1,766,130 | $0 | $1,766,130
Total Other | $1,517,000 | $1,757,000 | $1,349,000 | $930,000 | $5,553,000 | ($2,600) | ($1,293,840) | $4,256,560 | $741,055 | $3,515,505
Contingency |  |  |  |  | $500,000 |  |  | $500,000 |  | $500,000
Total ERP by FY | $3,877,735 | $4,371,203 | $2,072,700 | $1,092,250 | $11,913,888 | $156,400 | ($4,415,503) | $7,654,785 | $3,344,280 | $4,310,505
We have the funding in the project budget to cover the extension

## Slide 9
ERP Project Requests of the Board
  Approve an additional $6,473,475 to provide the spending authority to cover FY 2022 POs carried-forward into FY 2023
  At the January / February board meetings approve the additional negotiated cost for the ERP Project resulting from the 2-month extension to go-live and 2 additional months of post-implementation support
Board Request

## Slide 10
Questions?