## Slide 1
City of Stamford, Connecticut
Board Of Finance
ERP Project Extension Change Order
January 19, 2023
Innovating Since 1641

## Slide 2: Project Extension Drivers
Prior Year Purchase Orders
  Treatment in H T E vs. Oracle
User Acceptance Testing Conversion Status
  Significant volume of budget errors
  Conversion restart
Project team preparedness
Notes: Todd
Acknowledging the fact that the BOF got this project started and Board member participation
The board participants are the watch dogs that will report back to the boards on our progress and issues

## Slide 3: Project Extension Cost
ISG Conversion and Interface support: $60,000
Oracle / Sierra-Cedar: (Implementation) $725,000*
Oracle / Sierra-Cedar: (Additional post Go-live Support) $425,000*
CanAm: $5,100
      Total $1,215,100
      * $1,150,000 Approval requested today.
Notes: Todd
Acknowledging the fact that the BOF got this project started and Board member participation
The board participants are the watch dogs that will report back to the boards on our progress and issues

## Slide 4: Change Order Details
  The ERP project has extended the go-live date from January 1, 2023, to March 1, 2023, as a result of the discovery of how the Oracle financial system treats POs carried forward from prior years. The amendment includes the removal of the implementation services for the inventory module from the ERP project scope. The inventory module will be included in the scope of a new work order system that is being considered by the Office of Operations which will be addressed in a future amendment.
  Amendment 2 to the Oracle Services Agreement increases the cost of the project due to the following:
  Amendment Section 2 a.
  Division of the ERP project into two waves to coincide with the schedule under which the project has been working. Wave 1 is the financial, procurement, and projects and grants modules and Wave 2 is the Enterprise Performance Management module for budget development and narrative reporting (budget book).
  Extension of the Wave 1 go-live date by 2 months from January 1, 2023, to March 1, 2023
  Amendment Section 2 b.
  Removal of the inventory module from the implementation services described in the original agreement
  Amendment Section 2 c.
  Addition of 5 reports to the original 20 to be developed by Sierra-Cedar adding
  Amendment Section 2 d.
  Removal of training for the inventory module described in the original agreement
  Amendment Section 2 e.
  Removal of the implementation services for the inventory module which has been removed from scope
  Amendment Section 2 f.
  Changes number of reports from 20 to 25
  Amendment Section 2 g.
  Adds deliverable D30 Enter UAT (Wave 1) to formally document the start of UAT
  Amendment Section 2 h.
  Changes to the per deliverable cost to the remaining Wave 1 deliverables to absorb the $725,000 of increased implementation fees
Notes: Todd
Acknowledging the fact that the BOF got this project started and Board member participation
The board participants are the watch dogs that will report back to the boards on our progress and issues

## Slide 5: Impact on Project Budget
Capitalized Implementation, Subscription, Travel, and Other Cost |  |  |  |  |  |  |  |  |  | 
Estimated Capital Cost by Fiscal Year |  |  |  |  |  |  |  |  |  | 
Cost Category | FY 21/22 | FY 22/23 | FY 23/24 | FY 24/25 | Total Budget | Adjustments | Actuals-to-Date | Unexpended | Encumbered | Available Balance
ERP Implementation | $1,997,500 | $1,402,500 |  |  | $3,400,000 | $159,000 | ($2,358,875) | $1,200,125 | $1,200,125 | $0
L&P Implementation |  | $470,000 | $509,000 |  | $979,000 |  | ($80,000) | $899,000 | $899,000 | $0
CanAm Cashiering Implementation | $88,500 | $53,260 |  |  | $141,760 |  | ($130,620) | $11,140 | $11,140 | $0
ERP Implementation Contingency |  | $100,000 |  |  | $100,000 |  |  | $100,000 |  | $100,000
Total Implementation | $2,086,000 | $2,025,760 | $509,000 | $0 | $4,620,760 | $159,000 | ($2,569,495) | $2,210,265 | $2,110,265 | $100,000
ERP Software Subscriptions | $198,100 | $330,013 |  |  | $528,113 |  | ($553,148) | ($25,035) | ($25,035) | $0
L&P Subscriptions |  | $123,525 | $164,700 | $137,250 | $425,475 |  |  | $425,475 | $425,475 | $0
CanAm Cashiering Subscriptions | $16,635 | $49,905 |  |  | $66,540 |  | ($133,080) | ($66,540) | ($66,540) | $0
Total Subscriptions | $214,735 | $503,443 | $164,700 | $137,250 | $1,020,128 | $0 | ($686,228) | $333,900 | $333,900 | $0
ERP Travel Expense (estimated) | $50,000 | $35,000 |  |  | $85,000 |  |  | $85,000 |  | $85,000
L&P Travel Expense (estimated) |  | $35,000 | $50,000 | $25,000 | $110,000 |  |  | $110,000 |  | $110,000
CanAm Cashiering Travel Expense (estimated) | $10,000 | $15,000 |  |  | $25,000 |  | ($25,000) | $0 | $0 | $0
Total Travel | $60,000 | $85,000 | $50,000 | $25,000 | $220,000 | $0 | ($25,000) | $195,000 | $0 | $195,000
ISG Project Management | $399,000 | $399,000 | $399,000 | $280,000 | $1,477,000 |  | ($831,250) | $645,750 | $645,750 | $0
ISG Consulting Conversion & Interface Resources | $208,000 | $92,000 |  |  | $300,000 | $146,400 | ($312,707) | $133,694 | $133,694 | $0
City Overtime | $200,000 | $450,000 | $200,000 | $150,000 | $1,000,000 |  |  | $1,000,000 |  | $1,000,000
Equipment Acquisition | $118,000 | $66,000 | $0 | $0 | $184,000 |  |  | $184,000 |  | $184,000
Fleet Maintenance and Fuel Dispensing Software | $592,000 | $0 | $0 | $0 | $592,000 |  | ($26,625) | $565,375 | $0 | $565,375
Ceridian Dayforce Integration |  |  |  |  |  | $77,400 | ($45,000) | $32,400 | $32,400 | $0
Contingent 3rd Party Consulting - Innovations |  | $750,000 | $750,000 | $500,000 | $2,000,000 | ($226,400) | ($37,560) | $1,736,040 | $0 | $1,736,040
Total Other | $1,517,000 | $1,757,000 | $1,349,000 | $930,000 | $5,553,000 | ($2,600) | ($1,253,142) | $4,297,259 | $811,844 | $3,485,415
Contingency |  |  |  |  | $500,000 |  |  | $500,000 |  | $500,000
Total ERP by FY | $3,877,735 | $4,371,203 | $2,072,700 | $1,092,250 | $11,913,888 | $156,400 | ($4,533,865) | $7,536,424 | $3,256,009 | $4,280,415
Project and Support Extension |  |  |  |  |  | $1,215,100 |  | $1,215,100 |  | $1,215,100
Projected Balance after Board Approval |  |  |  |  |  |  |  | $6,321,324 |  | $3,065,315
Notes: Todd
Acknowledging the fact that the BOF got this project started and Board member participation
The board participants are the watch dogs that will report back to the boards on our progress and issues

## Slide 6: Future Budget Impacts
Current Projected Budget Balance: | $3,065,315
Work Order and Inventory Implementation Services (incl. Inventory module implementation services of $125,000): | $1,300,000
Human Resources System Requirements Development and Selection: | $410,000
Remaining ERP Budget: | $1,355,315
HR system implementation costs to be determined | 
Notes: Todd
Acknowledging the fact that the BOF got this project started and Board member participation
The board participants are the watch dogs that will report back to the boards on our progress and issues

## Slide 7
Questions?